ANALYST RECOMMENDATION BRIEF

Internal — Strategic Initiative Review

# GKMS Digital Remittance Crossover — Branch Footprint Optimization

Prepared for: GKFG Executive Committee  |  Prepared by: Money Services Strategy  |  Confidence: Medium-High

RECOMMENDATION Begin a 24-month rationalization of the GKMS branch footprint in Trinidad & Tobago and Guyana, redirecting saved capacity into GK One digital remittance acceleration. Three-year net margin uplift: +US$5.4M. Branch footprint reduced from 38 to 22 locations.

## Strategic Rationale

Digital remittance is steadily displacing in-person volume across our T&T and Guyana corridors. GK One adoption among existing GKMS customers in these markets has reached 31% and is growing. Each in-person transaction carries roughly 2.2x the cost-to-serve of a digital one. With branch leases coming up for renewal across 16 locations in the next 24 months, this is a once-a-cycle opportunity to right-size the cost base and accelerate the platform shift.

## Market Context

- Current GKMS branch network in T&T + Guyana: 38 locations

- Current digital remittance share of total volume: 31% (Jamaica reference: 58%)

- Projected digital share by Year 3: 61% (assumes 30% YoY shift, mirroring Jamaica’s 2021–2024 trajectory)

- Branch leases up for renewal in next 24 months: 16 of 38 locations

## Three-Year Financial Projection

| Metric | Year 1 | Year 2 | Year 3 |
| --- | --- | --- | --- |
| Branch count (end of year) | 32 | 26 | 22 |
| Digital share of remittance volume | 40% | 51% | 61% |
| Branch operating cost (US$M) | (8.4) | (7.0) | (6.0) |
| One-time rationalization cost (US$M) | (1.8) | (0.9) | (0.4) |
| Digital margin gain (US$M) | 1.2 | 3.4 | 5.6 |
| Net margin uplift vs. status quo (US$M) | (0.4) | 2.1 | 3.7 |

## Key Modelling Inputs

- Year-over-year shift from in-person to digital: 30% (mirrors Jamaica 2021–2024 actual)

- Digital margin per transaction relative to in-person: 62% at scale (Jamaica current state)

- Branch fixed-cost flexibility: assumes 18-month notice period for lease + workforce rationalization

- Customer attrition during rationalization: assumed 4% of in-person-only customers per closure

- GK One platform marginal cost per incremental transaction: US$0.18

## Risks

- Customer disruption during transitions in semi-rural markets where the GKMS branch is the primary financial touchpoint. Mitigation: transition support program.

- Regulatory licensing implications of branch closures in some territories. Mitigation: legal review underway.

- Competitive response: digital-native remittance providers may accelerate marketing. Mitigation: GK One feature roadmap.

## Decision Requested

Approval to proceed with the 24-month rationalization plan, with US$3.1M of one-time transition cost authorization across the three-year period, and quarterly review of customer attrition metrics.

## Your Charge

Find the three assumptions inside this brief that, if changed by a reasonable amount, would flip the recommendation from EXPAND to HOLD or CONTRACT. For each, write on your worksheet:

- The assumption (the specific number or premise)

- How much it would have to change (e.g., “digital margin holds at 45% of in-person rather than 62%”)

- Why this is plausible (what real-world condition would cause it)

- How the recommendation flips (the new recommended action)

You have 15 minutes. Nominate one presenter. You will have 3 minutes to report back.

### Hint: Look in three categories

- Customer behavior assumptions: how customers will respond

- Market condition assumptions: external factors outside GKFG control

- Cost or capacity assumptions: how flexible our cost base really is